## IT2151-03-Green Supply Chain Co
State | Work Item Type | Sprint ID | Sprint Goal | Product Backlog | Tasks | User Stories | Acceptance Criteria | Assigned To | Priority | Story Points | Definition of Done | Task Estimated Hours (In Hours)
New | Product Backlog Item | 52 | The Goal of this sprint is to lay the groundwork/foundations that will allow for the essential basic functions of the platform to function properly for continuous development. For example, to manage and configure the server, database, basic features of the website such as the search, company detailed page and the relevant functions with the pages, basic analytics tasks, etc. As well as to have communications and other important functions work properly | High Performance During Peak Usage |  | As a system, I want to have High or usual performance during peak hours of usage so that I have a consistent experience with the platform. | <ol><li>Design for high availability and performance, especially under peak loads. </li><li>Ensure responsiveness under peak loads.<br> </li><li>Implement mechanisms for auto-scaling.<br> </li> </ol> | Don Tan <DonTJunZ@gmail.com> | 4 | 8 | 1. The Server should be able to handle high loads at peak usage. 2. The Server should auto-scale itself to reduce excessive power usage.
To Do | Task | 54 |  |  | Design system for high availability |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 4
New | Product Backlog Item | 145 |  | Platform Data Storage |  | As an System, I want to have my Data stored properly, so that I can call upon said data when necessary. | <ol><li>Database is to be created and accessible by the system, users and admins. </li><li>A Server is to be created to be the middleman for the database and platform. </li><li>A server is to be established to act as an intermediary between the database and the platform, as well as to receive data from other actors in the system, such as sensors.<br> </li><li>Both Server and Database need to be managed and maintained properly. </li> </ol> | Don Tan <DonTJunZ@gmail.com> | 4 | 8 | 1. Database and Server are to be created and accessible. 2. The Server is to serve as a middleware between the Database, Platform(Front-end) and other data inputs(i.e. Sensors). 3. The Database and Server need to be managed and maintained properly(i.e. Proper documentation, procedures and regular intervals of checks).
To Do | Task | 146 |  |  | Database Creation |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 3
To Do | Task | 147 |  |  | Server Creation |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 3
To Do | Task | 148 |  |  | Middleware implementation(Making the Server an Intermediary) |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 4
To Do | Task | 153 |  |  | Creation of Database and Server Management Systems/Documentation |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 2
New | Product Backlog Item | 29 |  | Integration of Smart Meters and Sensors |  | as a Admin, I want to Allow integration of various smart meters and sensors, so that we can keep track of our sustainability goals.<br> | <ol><li>&nbsp;Accept various data formats (i.e.. Analog, Digital.). </li><li>Reliably transmit the data across the platform. </li><li>&nbsp;keep track of the transmitted data, for example it keeps tracks of carbon emissions&nbsp; </li><li>Creation of Resource checking page </li> </ol> | Don Tan <DonTJunZ@gmail.com> | 2 | 8 | 1. The Server is to be configured to accept various inputs, specifically, Analog and/or Digital. 2. Keep Track of the transmitted data, for example, the tracking of carbon emissions or usage of a resource of sorts. 3. Creation of a “Page” or Section that provides access to the resources.
To Do | Task | 67 |  |  | Enable the system to allow for multiple data formats(i.e. Analog, digital) |  |  | Don Tan <DonTJunZ@gmail.com> | 2 |  |  | 7
New | Product Backlog Item | 150 |  | Platform Homepage Creation |  | As a user, I want to have a Homepage , so that I can easily navigate and access the resources provided by the platform. | <ol><li>Homepage has to be designed and created. </li><li>Navigation has to be planned out properly and be intuitive. </li> </ol> | Clarance Lim <clarancelimck@hotmail.com> | 4 | 2 | 1. Homepage has to be designed and created without any errors. 2. The navigation must be meticulously planned and intuitive, clearly reflecting the purpose of each navigation button.
To Do | Task | 151 |  |  | Planning of Homepage |  |  | Clarance Lim <clarancelimck@hotmail.com> | 2 |  |  | 1
To Do | Task | 152 |  |  | Planning of Navigation with regards to Homepage |  |  | Clarance Lim <clarancelimck@hotmail.com> | 2 |  |  | 1
To Do | Task | 173 |  |  | Creation of Frontend Homepage |  |  | Clarance Lim <clarancelimck@hotmail.com> | 2 |  |  | 3
To Do | Task | 174 |  |  | Creation of Backend Homepage |  |  | Clarance Lim <clarancelimck@hotmail.com> | 2 |  |  | 3
New | Product Backlog Item | 39 |  | User Authentication(Registration) |  | As a visitor, I want to create a new account by providing my personal details, so I can access the system.<br> | <ol><li>Users can access the registration page from the homepage. </li><li>Users must provide a valid email address, unique username, and secure password. </li><li>Upon successful registration, users receive a confirmation email. </li><li>Users are redirected to the login page after registration. </li> </ol> <br> | Hng Wu Tan <hngwutan@gmail.com> | 4 | 5 | 1. Users can access an account creation form. 2. The form includes fields for necessary information (e.g., name, email, password). 3. The system validates input data and provides error messages for invalid entries. 4. Successful account creation redirects users to a confirmation page. 5. Account data is saved in the database. 6. Unit tests cover account creation functionality. 7. UAT is passed. 8. Documentation for account creation is updated.
To Do | Task | 86 |  |  | Design the sign up page UI. |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 1
To Do | Task | 87 |  |  | Implement form fields for username and password on the UI |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 1
To Do | Task | 88 |  |  | Create backend API for user authentication. |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 2
To Do | Task | 89 |  |  | Redirect users to the company selection page upon successful registration. |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 0.1
New | Product Backlog Item | 35 |  | User Authentication(Login) |  | As a registered user, I want to log in using my email and password, so I can access the system with my account.<br> | <ol><li>Users can access the login page from the homepage. </li><li>Users must enter their email and password correctly to log in. </li><li>Users are redirected to their dashboard upon successful login. </li><li>Users receive an error message if login credentials are incorrect. </li> </ol> <br> | Hng Wu Tan <hngwutan@gmail.com> | 4 | 3 | 1. Users can enter their email and password to log in. 2. The system verifies credentials against the database. 3. Successful logins redirect users to their dashboard. 4. Failed login attempts show appropriate error messages. 5. Login attempts are logged for security monitoring. 6. Unit tests cover login functionality. 7. UAT is passed. 8. Security best practices are implemented (e.g., password hashing). 9. Documentation is updated for the login process.
To Do | Task | 78 |  |  | Design the login page UI. |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 1
To Do | Task | 82 |  |  | Implement form fields for username and password with validation on the UI |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 1
To Do | Task | 83 |  |  | Create backend API for user authentication |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 2
To Do | Task | 85 |  |  | Redirect users to the home page upon successful login. |  |  | Hng Wu Tan <hngwutan@gmail.com> | 2 |  |  | 0.1
New | Product Backlog Item | 143 |  | Organization Join Request |  | As a User, I want to be able to request to join and gain access to a Organization/Company communications channels, so that I can collaborate with my colleagues and superiors. | <ol><li>The system should allow users to view the company when clicking on it. </li><li>The system should allow users to request to join companies that are found with the search functionalities. </li><li>The system should provide the option for users to take back join requests. </li> </ol> | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 | 2 | 1. Users can request to join companies found with the search functionalities. 2. Users can view detailed information about a company when clicking on it, including relevant company information (name, industry, location, size). 3. Users can retract or cancel their join requests if necessary. 4. Company page frontend is updated with the backend when user open company page. 5. Comprehensive testing ensures all functionalities (view company, request to join, retract join request) work correctly and meet requirements. 6. User acceptance testing validates that the system meets user needs is a pass. 7. Update relevant documentation, including user manuals or help guides, to reflect changes related to organization join requests.
To Do | Task | 177 |  |  | Plan Company UI Interface |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 |  |  | 1
To Do | Task | 175 |  |  | Create Frontend Company Page |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 |  |  | 2
To Do | Task | 176 |  |  | Create Backend Company Page |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 |  |  | 2
To Do | Task | 155 |  |  | Implement request to join functionality |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 |  |  | 4
New | Product Backlog Item | 41 |  | Display Search Results |  | As a user, I want to see the search results displayed in an organized manner so that I can easily review and select relevant companies.<br> | <ol><li><span>Display a list of companies matching the search criteria.</span> </li><li>Include key details (name, industry, location, size) for each company in the results. </li><li>Enable pagination for search results. </li><li>Allow users to click on a company to view detailed information. </li><li><span>Provide options to view results in different formats (list, grid).</span> </li> </ol> | Terrence Cheong <terrencecheongyeehong@gmail.com> | 2 | 3 | 1. Display a list of companies matching the search criteria. 2. Include key details (name, industry, location, size) for each company in the results. 3. Enable pagination for search results. 4. Allow users to click on a company to view detailed information. 5. Provide options to view results in different formats (list, grid). 6. Perform comprehensive testing to ensure all functionalities (display results, pagination, detailed view, format options) work correctly and meet requirements. 7. Update relevant documentation, including user manuals or help guides, to reflect changes related to displaying search results.
To Do | Task | 102 |  |  | Allow users to click on a company to view detailed information |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 2 |  |  | 3
New | Product Backlog Item | 144 |  | Organization Accepting of join request |  | As an Admin/Owner of an Organization/Company, I want to be able to accept join requests so that my colleagues can collaborate with me and each other.&nbsp; | <ol><li><span style="font-weight:inherit;">The system should allow admins to accept join requests.</span> </li><li><span style="font-weight:inherit;">The system should provide an option to decline join requests.</span> </li><li><span style="font-weight:inherit;">The system should grant access to the user that is accepted.</span> </li> </ol> | Terrence Cheong <terrencecheongyeehong@gmail.com> | 4 | 3 | 1. The system allows admins to accept join requests. 2. The system provides an option for admins to decline join requests. 3. The system grants access to the user upon acceptance of the join request. 4. Comprehensive testing ensures all functionalities (accept join requests, decline join requests, grant access) work correctly and meet requirements. 5. Relevant documentation, including admin manuals or help guides, is updated to reflect changes related to accepting join requests.
To Do | Task | 164 |  |  | Implement ability to accept join requests |  |  | Terrence Cheong <terrencecheongyeehong@gmail.com> | 2 |  |  | 3
New | Product Backlog Item | 30 |  | Team Communication on Sustainability Progress |  | As an admin, I want to allow team communication on sustainability progress, so that no issues of miscommunication occur during the project. | <ol><li>Include messaging function for team communication </li><li>support both individual and group messages </li><li>maintain a log of all interactions </li> </ol> | shjazk56 <shjazk56@gmail.com> | 4 | 5 | 1. Admins and users should have access to the message function for communication.Admins and users should be able to message others individually or in a group chat. 2. Admins and users should be able to view the logs of all interactions in the messaging function.
To Do | Task | 60 |  |  | Creating a Messaging Function |  |  | shjazk56 <shjazk56@gmail.com> | 4 |  |  | 5
New | Product Backlog Item | 33 |  | Coordination with external partners |  | As an admin I want to coordinate with external consultants and partners so that we can work together to complete the project. | 1.Support inviting external users 2. Grant appropriate access levels 3.Enable seamless collaboration through shared documents and communication tools | shjazk56 <shjazk56@gmail.com> | 4 | 3 | 1. Admins should be able to invite external partners or collaborators to participate. 2. Admins should be able to grant the appropriate access levels needed for each user to do their job. 3. Admins and users should be able to work together by sharing work and information while communicating with one another.
To Do | Task | 65 |  |  | Coordination with External Partners |  |  | shjazk56 <shjazk56@gmail.com> | 4 |  |  | 1
New | Product Backlog Item | 34 |  | Predictive Analytics for Resource Usage |  | As an admin, I want to use historical data to forecast future usage, so that I can optimize supply chain operations, reduce waste, and enhance sustainability. | <ol><li>Present predictions in an easy-to-understand format<br> </li><li>Ensure that the forecasting system can provide real-time updates<br> </li> </ol> | Clarance Lim <clarancelimck@hotmail.com> | 3 | 3 | 1. Users/Customers can understand the predictions easily 2. There is real-time updates for the forecasting system
To Do | Task | 68 |  |  | Create simple, easy and intuitive charts, graphs, and dashboards to display forecasted resource usage. |  |  | Clarance Lim <clarancelimck@hotmail.com> | 2 |  |  | 4